## M-1
FORM M-1
PRICE VALUE SUMMARY
1 | D&C Price | From Bottom of Form M-2, Col. E | 0
2 | ATC Adjustments To Price | From Bottom of Form M-1.2 | 0
3 | Adjustments To D&C Price For Avoided Schematic Row | From Bottom of Form M-1.3 | 0
4 | Adjustments To D&C Price For Advancement Or Delay Of NTP 3 | From Bottom of Form M-1.4 | 0
5 | Factored Annual Maintenance Price | From Bottom of Form N-1 | 0
| PRICE VALUE |  | 0

## M-1.1
FORM M-1.1
D&C PRICE SUMMARY
ITEM / LINE NO. | DESCRIPTION | Maximum Price (Not to Exceed) |  | Item Total * (YOE$)
A | NTP 1 Work Effort
1 | Project Management Plan (PMP)
1a | Project Administration | 1000000
1b | QMP General Requirements | 400000
1c | Professional Services Quality Management Plan | 500000
1d | Construction Quality Management Plan | 600000
1e | Environmental Management Plan | 600000
1f | Public Involvement Plan | 300000
1g | Safety Management Plan | 400000
2 | Transportation Management Plan (TMP) | 500000
3 | Collocation Office Elements
3a | Initial Core Office Lease & Equipment | 2500000
3b | Collocated Office Layout Plan | 200000
3c | Network Administration Plan & Setup | 300000
4 | Existing Conditions Site Documentation | 300000
5 | Project Baseline Schedule | 1500000
6 | Segment Limits Map | 200000
7 | Submittal Schedule | 200000
8 | ROW Activity Plan | 300000
9 | DBE Utilization Plan | 500000
10 | OJT Utilization Plan | 200000
11 | Enter portions of the Project ROW that ADOT owns, or is in possession of, to conduct surveys and site investigations, including geotechnical, Hazardous Materials and Utilities investigations, | 600000
12 | Commence ROW acquisition services (but only after ADOT approves the ROW Activity Plan); | 600000
13 | Commence negotiating with the Union Pacific Railroad; | 100000
14 | Commence negotiating Utility Agreements with Utility Owners | 200000
15 | Pre-NTP 2 Design Work | 15000000
16 | Subtotal "Maximum Price" Items (other than mobilization) | 27000000 |  | 0
17 | NTP 1 mobilization - Includes SWPPP, Noxious Species Control Plan, Basis of Design Report, preparation of bulletin boards, sample Vehicle Project Logo, bat survey, Plant Inventory, Sign Inventory, ITS Inventory; Not to exceed 1% of D&C Price (other than mobilization)
18 | D&C bond and insurance premiums to the extent payable per 13.3.4.3 of the Agreement
19 | Subtotal NTP 1 Work (Sum Line 17 + Line 18) |  | Subtotal "A" | 0
*Proposers shall bid each of the line items indicated, in no instance more than the applicable “Maximum Price”. The bid amounts for the line items are part of, and shall be included in, Proposer’s lump sum D&C Price. Developer will bear the risk that its actual cost for a line item incurred prior to NTP 2 exceeds the line item bid amount. The Developer will be paid according to the terms of the Agreement.
B | Professional Services
20 | Development Management
21 | Project Design, Design Survey
22 | Environmental Permitting
23 | Right-of-Way Acquisition Services & ROW Survey/Mapping
24 | Utility Locates, Utility Survey, and Utility Adjustment Design
25 | Professional Services IQF, Construction IQF
26 | Community Outreach, Public Involvement
27 | Miscellaneous Professional Services not covered by Lines 20 - 26
28 | Subtotal Professional Services (Sum Lines 20 through 27) |  | Subtotal "B" | 0
C | Construction
29 | Construction Management
30 | Mobilization, not including NTP 1 mobilization; Not to exceed 4% of D&C Price (other than mobilization)
31 | Traffic Control
32 | Roadway
33 | Bridges
34 | Elwood Street pedestrian bridge
35 | Pedestrian bridge aesthetic treatments | 600000 |  | 600000
36 | Durango Street connector
37 | Walls & Noise Barriers
38 | Roadway Lighting
39 | Signing
40 | Drainage
41 | FMS
42 | Landscape
43 | Developer-Designated ROW
44 | Environmental Mitigation
45 | Utility Adjustments
46 | Engineer's Field Office
47 | Warranty Bond Premiums
48 | Other Insurance Coverages Not Required in NTP 1
49 | Miscellaneous Construction Items not covered by Lines 29 - 48)
50 | Subtotal Construction (Sum Lines 29 through 49) |  | Subtotal "C" | 0
| Total Price (Line 19 + Line 28 + Line 50) |  | TOTAL | 0
*Note: Proposer shall enter amounts in year-of-expenditure dollars. |  |  | Check for match w/ Form M-2 | OK
Item Description for Elements Contained in Category ‘A’
A-1a | Project Administration
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Project Administration section of the Project Management Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-1b | QMP General Requirements
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the QMP General Requirements, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-1c | Design Quality Management Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Design Quality Management Plan , as specified in the Contract Documents with no additional compensation being allowed therefor.
A-1d | Construction Quality Management Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Construction Quality Management Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-1e | Environmental Management Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Environmental Management Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-1f | Public Involvement Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Public Involvement Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-1g | Safety Management Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Safety Management Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-2 | Transportation Management Plan (TMP)
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Transportation Management Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-3a | Initial Core Office Lease & Equipment
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to the initial core office lease and equipment, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-3b | Core Office & Layout Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to the Core Office & Layout Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-3c | Network Administration Plan & Setup
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Network Administration Plan and setup, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-4 | Site Documentation
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Site Documentation Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-5 | Project Baseline Schedule
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Project Baseline Schedule, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-6 | Segment Limits Map
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Segment Limits Map, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-7 | Submittal Schedule
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the Submittal Schedule, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-8 | ROW Activity Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the ROW Activity Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-9 | DBE Utilization Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the DBE Utilization Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-10 | OJT Utilization Plan
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to development of the OJT Utilization Plan, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-11 | Enter portions of the Project ROW that ADOT owns, or is in possession of, to conduct surveys and site investigations, including geotechnical, Hazardous Materials and Utilities investigations,
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to entering portions of the Project ROW that ADOT owns, or is in possession of, to conduct surveys and site investigations, including geotechnical, Hazardous Materials and Utilities investigations, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-12 | Commence ROW acquisition services (but only after ADOT approves the ROW Activity Plan)
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to commencing ROW acquisition services (but only after ADOT approves the ROW Activity Plan), as specified in the Contract Documents with no additional compensation being allowed therefor.
A-13 | Commence negotiating with the Union Pacific Railroad;
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to commencing negotiating with the Union Pacific Railroad, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-14 | Commence negotiating Utility Agreements with Utility Owners
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to commencing negotiating Utility Agreements with Utility Owners, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-15 | Pre-NTP 2 Design Work
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to pre-NTP 2 Design Work, as specified in the Contract Documents with no additional compensation being allowed therefor.
A-17 | NTP 1 mobilization - Includes SWPPP, Noxious Species Control Plan, Basis of Design Report, preparation of bulletin boards, sample Vehicle Project Logo, bat survey, Plant Inventory, Sign Inventory, ITS Inventory; Not to exceed 1% of D&C Price (other than mobilization)
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to NTP 1 Mobilization, including SWPPP, Noxious Species Control Plan, Basis of Design Report, preparation of bulletin boards, sample Vehicle Project Logo, bat survey, Plant Inventory, Sign Inventory, ITS Inventory; as specified in the Contract Documents with no additional compensation being allowed therefor.
A-18 | D&C bond and insurance premiums to the extent payable per 13.3.4.3 of the Agreement
Includes full compensation for D&C bond and insurance premirums to the extent payable per Section 13.3.6.3 of the Agreement with no additional compensation being allowed therefor.
Item Description for Elements Contained in Category ‘B’
B-20 | Professional Services Management
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the Professional Services management provisions and requirements as specified in the Contract Documents with no additional compensation being allowed therefor.
B-21 | Project Design, Design Survey, Site Investigation
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the design, design survey, geotechnical engineering and site condition investigation provisions and requirements as specified in the Contract Documents, with no additional compensation being allowed therefor.
B-22 | Environmental Permitting
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the environmental permitting and governmental approval activities provisions and requirements as specified in the Contract Documents with no additional compensation being allowed therefor.
B-23 | Right-of-Way Acquisition Services
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the Right-of-Way acquisition activities provisions and requirements as specified in the Contract Documents with no additional compensation being allowed therefor.
B-24 | Utility Locates, Utility Survey, and Utility Adjustment Design
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the utility location, utility survey, utility relocation design and utility coordination provisions and requirements as specified in the Contract Documents, with no additional compensation being allowed therefor.
B-25 | Professional Services IQF, Construction IQF
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the Professional Services IQF and Construction IQF provisions and requirements as specified in the Contract Documents, with no additional compensation being allowed therefor.
B-26 | Community Outreach, Public Involvement
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the community outreach and public involvement requirements and provisions as specified in the Contract Documents, with no additional compensation being allowed therefor.
B-27 | Miscellaneous Professional Services
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with miscellaneous Professional Services, which are not included in other items, as specified in the Contract Documents, with no additional compensation being allowed therefor.
Item Description for Elements Contained in Category 'C'
C-29 | Construction Management
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with the construction management provisions and requirements as specified in the Contract Documents with no additional compensation being allowed therefor.
C-30 | Mobilization, not including NTP 1 Work; Not to exceed 4% of D&C Price (other than mobilization)
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with provisions and requirements related to mobilization, not including NTP 1 mobilization, as specified in the Contract Documents.
C-31 | Traffic Control & Management
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with the traffic control and management requirements for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-32 | Roadway
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all roadways (complete in place), including pavement construction, earthwork construction, roadway barriers, guardrails, fencing, demolition and roadway preparation for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-33 | Bridges
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all bridges for the Project (except for the Elwood Street pedestrian bridge), including associated aesthetics and foundation elements, as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-34 | Elwood Street pedestrian bridge
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with designing and constructing the Elwood Street pedestrian bridge (complete in place) for the Project, as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-35 | Pedestrian bridge aesthetic treatments
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with pedestrian bridge aesthetic treatments (complete in place) for the Project, as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-36 | Durango Street connector
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with designing and constructing the Durango Street connector (complete in place) for the Project, including associated aesthetics and foundation elements, as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-37 | Walls & Noise Barriers
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all the work efforts associated with constructing all retaining walls and noise barriers (complete in place) for the Project, including associated aesthetics as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-38 | Roadway Lighting
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all roadway lighting and electrical improvements (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-39 | Signing
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all signing (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-40 | Drainage
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all drainage improvements (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-41 | FMS
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all FMS (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-42 | Landscape
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with construction activities related to the installation of landscaping, including plant establishment, provisions and requirements (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor. This item does not include the design of landscaping and aesthetics, which is included in item B-18.
C-43 | Developer-Designated ROW
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with all Developer-Designated ROW for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-44 | Environmental Mitigation
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with all environmental mitigation activities (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-45 | Utility Adjustments
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with constructing all utility adjustments (complete in place) for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-46 | Engineer's Field Office
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work efforts associated with providing and operating the Engineer's field offiee for the Project as specified in the Contract Documents, with no additional compensation being allowed therefor.
C-47 | Warranty Bond Premiums
Includes all cost and incidentals in association with securing and providing warranty bonds meeting all Project provisions and requirements as specified in the Contract Documents with no additional compensation being allowed therefor.
C-48 | Other Insurance Coverages Not Required in NTP 1
Includes all cost and incidentals in association with securing and providing other insurance coverages not required in NTP 1 meeting all provisions and requirements as specified in the Contract Documents with no additional compensation being allowed therefor.
C-49 | Miscellaneous Construction Items
Includes full compensation for furnishing all labor, materials, tools, equipment, and incidentals; performing all work effort in association with miscellaneous construction items, which are not included in other items, as specified in the Contract Documents, with no additional compensation being allowed therefor.

## M-1.2
FORM M-1.2
ATC ADJUSTMENTS TO PRICE
ATC No. | DESCRIPTION of ATC DEEMED ACCEPTABLE FOR INCLUSION IN PROPOSAL | Costs to ADOT ($)
Total |  | 0
(To Form M-1, Item #2)
Notes:
- List all acceptable ATCs which are incorporated into the Proposal, even if they do not result in additional costs to ADOT.
- Costs to ADOT refers to the additional cost associated with the ATC as determined by ADOT and as set forth in the ATC acceptance letter.
- Add additional rows if needed.

## M-1.3
FORM M-1.3
ADJUSTMENTS TO D&C PRICE FOR AVOIDED SCHEMATIC ROW
ROW Credits ID No. | ADOT Parcel Number | Description | Credit Amount (Enter as a number ≤ 0)
Total |  |  | 0
(To Form M-1, Item #3)
Notes:
- Credit is as determined by ADOT in the ROW Credits response letter.
- For ROW Credits ID No., list the ROW Credits identification name/number that was referenced in the subject line of the ADOT ROW Credits response letter.
- Show credit as a negative dollar amount
- See ITP Section 5.6.1.3 for how Adjustments for Avoided Schematic ROW will be evaluated in the Price Score.
- Add additional rows if needed.

## M-1.4
FORM M-1.4
ADJUSTMENTS TO D&C PRICE FOR ADVANCEMENT OR DELAY OF NTP 3
Advancement Credit (Assumes NTP 3 occurs between 1 and 180 Days before NTP3 Window)
| Month After NTP 1 | Per Diem Credit (YOE$) (Enter as a number ≤ 0) | Discount Factor at 4.5% Per Annum | PV of 30 Day Credit
A | B | C | D | E = 30 x C x D
Days 1 - 30 before NTP3 Window | 24 |  | 0.91573 | 0
Days 31 - 60 before NTP3 Window | 23 |  | 0.9191 | 0
Days 61 - 90 before NTP3 Window | 22 |  | 0.92247 | 0
Days 91 - 120 before NTP3 Window | 21 |  | 0.92586 | 0
Days 121 - 150 before NTP3 Window | 20 |  | 0.92926 | 0
Days 151 - 180 before NTP3 Window | 19 |  | 0.93268 | 0
0
Delay Cost (Assumes NTP 3 between 1 and 180 Days after NTP3 Window)
| Month After NTP 1 | Per Diem Cost (YOE$) | Discount Factor at 4.5% Per Annum | PV of 30 Day Cost
A | B | C | D | E = 30 x C x D
Days 1 - 30 after NTP3 Window | 27 |  | 0.90571 | 0
Days 31 - 60 after NTP3 Window | 28 |  | 0.90239 | 0
Days 61 - 90 after NTP3 Window | 29 |  | 0.89909 | 0
Days 91 - 120 after NTP3 Window | 30 |  | 0.8958 | 0
Days 121 - 150 after NTP3 Window | 31 |  | 0.89252 | 0
Days 151 - 180 after NTP3 Window | 32 |  | 0.88925 | 0
|  | PV Cost Subtotal for 180 days |  | 0
|  | Sum (Credit + Cost) * |  | 0
(To Form M-1, Item #4)
*Note: If calculation of credit + cost is less than $0, the effect on the Price Value will be $0.
-

## M-2
FORM M-2
D&C PRICE DRAWS/CASH FLOW AND MAXIMUM ALLOWABLE CUMULATIVE DRAW TABLE
(All figures are in US Dollars)
Months after NTP1 | Anticipated Draw / Cash Flow (YOE$) | Developer's Cumulative Draw / Max Allowable Cumulative Draw (YOE$) | Discount Factor at 4.5% Per Annum | PV of Anticipated Draw / Cash Flow | ADOT's Cumulative Indicative Cash Flow Schedule (YOE$)
A | B | C | D | E = B x D | F
1 |  | 0 | 0.99634 | 0 | 30175868.3443 | 2016-03-01
2 |  | 0 | 0.99269 | 0 | 45462483.4086 | 2016-04-01
3 |  | 0 | 0.98906 | 0 | 55266268.8284 | 2016-05-01
4 |  | 0 | 0.98543 | 0 | 64995804.9314 | 2016-06-01
5 |  | 0 | 0.98183 | 0 | 82620262.7055 | 2016-07-01
6 |  | 0 | 0.97823 | 0 | 97663666.3361 | 2016-08-01
7 |  | 0 | 0.97465 | 0 | 103740845.1068 | 2016-09-01
8 |  | 0 | 0.97108 | 0 | 131209104.188 | 2016-10-01
9 |  | 0 | 0.96753 | 0 | 145302318.7332 | 2016-11-01
10 |  | 0 | 0.96398 | 0 | 159865307.0967 | 2016-12-01
11 |  | 0 | 0.96045 | 0 | 174428295.4601 | 2017-01-01
12 |  | 0 | 0.95694 | 0 | 187581962.369 | 2017-02-01
13 |  | 0 | 0.95343 | 0 | 202392105.7317 | 2017-03-01
14 |  | 0 | 0.94994 | 0 | 216718058.3964 | 2017-04-01
15 |  | 0 | 0.94647 | 0 | 230900794.5516 | 2017-05-01
16 |  | 0 | 0.943 | 0 | 243157586.3328 | 2017-06-01
17 |  | 0 | 0.93955 | 0 | 257214180.3523 | 2017-07-01
18 |  | 0 | 0.93611 | 0 | 273895715.6496 | 2017-08-01
19 |  | 0 | 0.93268 | 0 | 303913643.9563 | 2017-09-01
20 |  | 0 | 0.92926 | 0 | 334976207.9278 | 2017-10-01
21 |  | 0 | 0.92586 | 0 | 365036753.7068 | 2017-11-01
22 |  | 0 | 0.92247 | 0 | 396099317.6784 | 2017-12-01
23 |  | 0 | 0.9191 | 0 | 427161881.6499 | 2018-01-01
24 |  | 0 | 0.91573 | 0 | 455218391.0436 | 2018-02-01
25 |  | 0 | 0.91238 | 0 | 486211947.5763 | 2018-03-01
26 |  | 0 | 0.90904 | 0 | 516163534.2413 | 2018-04-01
27 |  | 0 | 0.90571 | 0 | 547113507.1285 | 2018-05-01
28 |  | 0 | 0.90239 | 0 | 577065093.7935 | 2018-06-01
29 |  | 0 | 0.89909 | 0 | 608563443.7866 | 2018-07-01
30 |  | 0 | 0.8958 | 0 | 640061793.7798 | 2018-08-01
31 |  | 0 | 0.89252 | 0 | 670529463.2108 | 2018-09-01
32 |  | 0 | 0.88925 | 0 | 702002660.5687 | 2018-10-01
33 |  | 0 | 0.88599 | 0 | 732460593.4958 | 2018-11-01
34 |  | 0 | 0.88275 | 0 | 763933790.8537 | 2018-12-01
35 |  | 0 | 0.87952 | 0 | 795406988.2116 | 2019-01-01
36 |  | 0 | 0.8763 | 0 | 823834392.2769 | 2019-02-01
37 |  | 0 | 0.87309 | 0 | 855172863.5889 | 2019-03-01
38 |  | 0 | 0.86989 | 0 | 885418071.1802 | 2019-04-01
39 |  | 0 | 0.86671 | 0 | 916671452.358 | 2019-05-01
40 |  | 0 | 0.86353 | 0 | 946916659.9493 | 2019-06-01
41 |  | 0 | 0.86037 | 0 | 965343101.7222 | 2019-07-01
42 |  | 0 | 0.85722 | 0 | 979660584.5879 | 2019-08-01
43 |  | 0 | 0.85408 | 0 | 993513938.7396 | 2019-09-01
44 |  | 0 | 0.85096 | 0 | 1007827504.535 | 2019-10-01
45 |  | 0 | 0.84784 | 0 | 1021679342.4015 | 2019-11-01
46 |  | 0 | 0.84474 | 0 | 1035992908.1968 | 2019-12-01
47 |  | 0 | 0.84164 | 0 | 1050306473.9921 | 2020-01-01
48 |  | 0 | 0.83856 | 0 | 1063696583.9297 | 2020-02-01
49 |  | 0 | 0.83549 | 0 | 1077998128.4318 | 2020-03-01
50 |  | 0 | 0.83243 | 0 | 1091830985.309 | 2020-04-01
51 |  | 0 | 0.82938 | 0 | 1105202746.9569 | 2020-05-01
TOTAL | 0 |  |  | 0
| (For Comparison with Form M-1.1) |  |  | (To Form M-1, Item #1)
NOTE: Proposer shall complete this Form M-2 for all months after NTP 1 until the month after the month of Final Acceptance indicated in Proposer’s Form O (such last month is presumed to be the month of the Final D&C Payment).

## N-1
FORM N-1
MAINTENANCE PRICE SUMMARY
Year of Maintenance Period | Total Routine Maintenance (From N-1.1) | Routine Maintenance Escalation Factor | Total Capital Asset Replacement Work (From N-1.2) | Capital Asset Replacement Work Escalation Factor | Escalated Total Annual Maintenance | Discount Factor | Factored Annual Maintenance Price
A | B | C | D | E | F = (B * C) + (D * E) | G | H = F * G
|  | 2% |  | 3% |  | 4.5%
1 | 0 | 1.0824 | 0 | 1.1255 | 0 | 0.83856 | 0
2 | 0 | 1.1041 | 0 | 1.1593 | 0 | 0.80245 | 0
3 | 0 | 1.1262 | 0 | 1.1941 | 0 | 0.7679 | 0
4 | 0 | 1.1487 | 0 | 1.2299 | 0 | 0.73483 | 0
5 | 0 | 1.1717 | 0 | 1.2668 | 0 | 0.70319 | 0
6 | 0 | 1.1951 | 0 | 1.3048 | 0 | 0.6729 | 0
7 | 0 | 1.219 | 0 | 1.3439 | 0 | 0.64393 | 0
8 | 0 | 1.2434 | 0 | 1.3842 | 0 | 0.6162 | 0
9 | 0 | 1.2682 | 0 | 1.4258 | 0 | 0.58966 | 0
10 | 0 | 1.2936 | 0 | 1.4685 | 0 | 0.56427 | 0
11 | 0 | 1.3195 | 0 | 1.5126 | 0 | 0.53997 | 0
12 | 0 | 1.3459 | 0 | 1.558 | 0 | 0.51672 | 0
13 | 0 | 1.3728 | 0 | 1.6047 | 0 | 0.49447 | 0
14 | 0 | 1.4002 | 0 | 1.6528 | 0 | 0.47318 | 0
15 | 0 | 1.4282 | 0 | 1.7024 | 0 | 0.4528 | 0
16 | 0 | 1.4568 | 0 | 1.7535 | 0 | 0.4333 | 0
17 | 0 | 1.4859 | 0 | 1.8061 | 0 | 0.41464 | 0
18 | 0 | 1.5157 | 0 | 1.8603 | 0 | 0.39679 | 0
19 | 0 | 1.546 | 0 | 1.9161 | 0 | 0.3797 | 0
20 | 0 | 1.5769 | 0 | 1.9736 | 0 | 0.36335 | 0
21 | 0 | 1.6084 | 0 | 2.0328 | 0 | 0.3477 | 0
22 | 0 | 1.6406 | 0 | 2.0938 | 0 | 0.33273 | 0
23 | 0 | 1.6734 | 0 | 2.1566 | 0 | 0.3184 | 0
24 | 0 | 1.7069 | 0 | 2.2213 | 0 | 0.30469 | 0
25 | 0 | 1.741 | 0 | 2.2879 | 0 | 0.29157 | 0
26 | 0 | 1.7758 | 0 | 2.3566 | 0 | 0.27902 | 0
27 | 0 | 1.8114 | 0 | 2.4273 | 0 | 0.267 | 0
28 | 0 | 1.8476 | 0 | 2.5001 | 0 | 0.2555 | 0
29 | 0 | 1.8845 | 0 | 2.5751 | 0 | 0.2445 | 0
30 | 0 | 1.9222 | 0 | 2.6523 | 0 | 0.23397 | 0
[6 empty] | TOTAL | 0
(To Form M-1, Item #5)

## N-1.1
FORM N-1.1
ROUTINE MAINTENANCE BREAKDOWN (Enter figures in USD 2015$)
Year of Maintenance Period | Maintenance Elements |  | Administrative Elements |  |  | Total Routine Maintenance
| Landscape, Litter & Sweeping | All Other Maintenance | Bonds | Insurance | Other costs
A | B | C | D | E | F | G = B + C + D + E + F
1 | [5 empty] | 0
2 | [5 empty] | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
21 | [5 empty] | 0
22 | [5 empty] | 0
23 | [5 empty] | 0
24 | [5 empty] | 0
25 | [5 empty] | 0
26 | [5 empty] | 0
27 | [5 empty] | 0
28 | [5 empty] | 0
29 | [5 empty] | 0
30 | [5 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0
(Values to Form N-1, Column B)

## N-1.2
FORM N-1.2
CAPITAL ASSET REPLACEMENT WORK BREAKDOWN (Enter figures in USD 2015$)
Year of Maintenance Period | Paving | Sign Replacement | Handback Items | Total Capital Asset Replacement Work | Insurance*
A | B | C | D | E = B + C + D | F
1 |  |  |  | 0
2 |  |  |  | 0
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
16 |  |  |  | 0
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0
21 |  |  |  | 0
22 |  |  |  | 0
23 |  |  |  | 0
24 |  |  |  | 0
25 |  |  |  | 0
26 |  |  |  | 0
27 |  |  |  | 0
28 |  |  |  | 0
29 |  |  |  | 0
30 |  |  |  | 0
TOTAL | 0 | 0 | 0 | 0 | 0
(Values to Form N-1, Column D)
*In column F, indicate the portion of Column E that represents the cost of insurance required under Exhibit 12, Sections 4 and 12 of the DBM Agreement for the Capital Asset Replacement Work.