## Sheet1
Potential Inactive Project Phase Report at 05/31/2018
ADOT PROJECT MANAGER OR CONTACT | Project Phase | Federal Project Number | Authorization Date | Days Inactive | Description | Project Oversight | Amount Encumbered | Amount Inactive
Siva Sivakumar | F000201D | 082A204 | 2015-12-17 | 160 | Rain Valley Wash Bridge STR # 395 | ADOT | 0 | 15784.98
Trent Kelso | F011501R | 017A | 2017-12-05 | 161 | Central Ave. Op Structure | ADOT | 0 | 800000
Suzanne Deitering | F013101X | 040C225 | 2017-08-22 | 170 | Devil Dog - Williams | ADOT | 0 | 1449900
Angela Ringor | H394012X | 000A209 | 2006-12-26 | 169 | NTNL RCRTNL TRLS (STATE PRKS) | ADOT | 0 | 1067.6
Vicki Bever | H680602U | 086A | 2012-08-27 | 168 | WHY- TUCSON HWY | ADOT | 428575.72 | 934077.72
ADOT PMG | H683701X | AZ04001 | 2005-08-18 | 168 | SKY ISLAND PARKWAY SCENIC ROAD | ADOT | 0 | 67970.47
Eric Prosnier | H719401L | 303A | 2008-05-15 | 169 | SR 303L, RIGGS RD - SR 801 | ADOT | 97461.65 | 538122.93
Victor Yang | H7454T1D | 999A365 | 2012-01-17 | 162 | US 60 TO I-10 DESIGN CONCEPT REPORT FOR PINAL COUNTY | ADOT | 0 | 4944.64
Troy Sieglitz | H769602R | 010D205 | 2010-06-24 | 162 | I-10 / SR 87 TI | ADOT | 0 | 184822.81
ADOT PMG | H830701D | 092A202 | 2012-01-17 | 164 | SR92 - TAYLOR AVENUE | ADOT | 1 | 8440.5
Vicki Bever | H831001D | 999A326 | 2010-09-22 | 175 | TONTO NATIONAL FOREST, VARIOUS HIGHWAY ROUTES | ADOT | 0 | 404340.7
Adam McGuire | H839401D | B19A201 | 2011-09-13 | 163 | INTERNATIONAL BORDER - MARICOPA/SR 189 | ADOT | 0 | 29148.43
ADOT Resource Admin | H8451B1D | B10C200 | 2011-11-14 | 177 | SB10, SAN PEDRO RIVER BRIDGE REPLACE/REHAB | ADOT | 0 | 1
ADOT Resource Admin | H8451G1D | B10C200 | 2011-11-14 | 177 | SB10, SAN PEDRO RIVER BRIDGE REPLACE/REHAB | ADOT | 0 | -9.9476e-14
ADOT Resource Admin | H8451R1D | B10C200 | 2011-11-14 | 177 | SB10, SAN PEDRO RIVER BRIDGE REPLACE/REHAB | ADOT | 0 | -1.0232e-12
ADOT PMG | H846801D | 086A216 | 2012-05-14 | 162 | SR 86, SAN ISIDRO SEGMENT | ADOT | 1681.78 | 354495.42
Adrian N. Leon | H855902R | 077A212 | 2015-06-30 | 177 | SR-77, NEAR SUMMIT | ADOT | 0 | 22394.5
Suzanne Deitering | H859001R | 191C220 | 2016-11-21 | 163 | SMELTER HILL-HORSESHOE CURVE, CLIFTON | ADOT | 0 | 2440.49
Mike Andazola | H8630CAX | 010A223 | 2014-06-20 | 163 | TYSON WASH BRIDGES (STR # 791,792) | ADOT | 0 | 10436.87
Mohammad Zaid | H867301X | 888A219 | 2017-01-06 | 160 | SR 202L, Dobson Rd to Ray Rd | ADOT | 0 | 164092
Jeff Davidson | H885901D | 070A220 | 2015-09-01 | 162 | SAN CARLOS HIGH SCHOOL - BIA 170, SAN CARLOS TRIBE | ADOT | 1 | 27959.15
Tafwachi Katapa | H891502D | 024A200 | 2017-11-30 | 177 | ELLSWORTH ROAD-IRONWOOD ROAD INTERIM PHASE II | ADOT | 0 | 1468692
Tricia Brown | H894401U | S40A201 | 2017-07-24 | 176 | WEST WINSLOW SPUR RR OP #1829 | ADOT | 268400 | 272381
Angela Ringor | M471609P | 917D003 | 2016-11-03 | 162 | 2017 ASP REC TRAIL PROJECTS | State Parks | 0 | 76745.04
Angela Ringor | M471801P | RTPA301 | 2017-11-22 | 177 | 2018 - PROGRAM OF PROJECTS | State Parks | 0 | 83452
Angela Ringor | M471802P | RTPA302 | 2017-11-22 | 177 | 2018 - PROGRAM OF PROJECTS | State Parks | 0 | 52872
Angela Ringor | M471812P | RTPA312 | 2017-11-22 | 177 | 2018 - PROGRAM OF PROJECTS | State Parks | 0 | 84836
Angela Ringor | M471815P | RTPA315 | 2017-11-22 | 171 | 2018 - PROGRAM OF PROJECTS | State Parks | 0 | 77103
David Riley | M589101X | 999M521 | 2016-08-26 | 154 | SHRP2 Software traffic data analysis | ADOT | 0 | 0
Angela Ringor | MPARKM2P | 999M137 | 2014-11-20 | 162 | SW RECREATIONAL TRAILS | State Parks | 0 | 5297.15
Angela Ringor | MPARKN1P | 999M098 | 2013-08-15 | 162 | SW RECREATIONAL TRAILS | State Parks | 0 | 9798.92
Angela Ringor | P030021P | 0001186 | 2014-07-09 | 164 | SPR PLANNING PRGM FY95 | ADOT | 0 | 1741.16
Angela Ringor | P180702P | MPDS018 | 2017-10-06 | 167 | 2018 WP MAJOR PROJECT | ADOT | 0 | 400000
Angela Ringor | P180703P | MPDS018 | 2017-10-06 | 167 | 2018 WP MAJOR PROJECT | ADOT | 0 | 400000
Angela Ringor | P181203P | MPDS018 | 2017-07-24 | 178 | 2018 WP MPD-Systems and Regional Planning & Progra | ADOT | 473602.46 | 478752.46
Angela Ringor | P860037P | 0001186 | 2014-07-09 | 176 | FY 2015 MPD PROGRAM OF PROJECTS | ADOT | 0 | 26785.87
Angela Ringor | PCG1501P | 999A472 | 2015-04-07 | 162 | CAG 2015 WORK PROGRAM | CAG | 0 | 0
Angela Ringor | PFM1408P | 999A443 | 2014-05-16 | 162 | FMPO STP FY 2014 | FMPO | 27725.2 | 32240.06
Angela Ringor | PFM1411P | 999A451 | 2014-06-17 | 161 | FMPO STP FY 2014 | FMPO | 0 | 484.29
Angela Ringor | PMG1801P | MAGS018 | 2017-06-21 | 163 | 2018 WP MAG | MAG | 1913.12 | 2391.4
Angela Ringor | PSC1701P | SCMS017 | 2016-09-01 | 175 | 2017 WP SCMPO | SCMPO | 0 | 0.32
Angela Ringor | PSC1803P | SCMT018 | 2017-12-13 | 163 | 2018 WP SCMPO | SCMPO | 36000 | 38176
Angela Ringor | PSEAG22P | 000H188 | 2015-08-13 | 177 | SEAGO SPR FUNDS | SEAGO | 0 | 0
Angela Ringor | PSHSP00P | 999a491 | 2015-07-31 | 177 | SEAGO 2016 WP HSIP FUNDS | SEAGO | 0 | 0
Angela Ringor | PSRTSA2P | 999A208 | 2009-08-10 | 164 | STATEWIDE SAFE ROUTES TO SCHOOL | ADOT | 1 | 16936.62
Angela Ringor | PYM1702P | YMPP017 | 2016-11-09 | 171 | 2017 WP YMPO | YMPO | 0 | 40383.77
Angela Ringor | R039629P | MPDR018 | 2017-06-14 | 177 | SPR-PART II RSRCH PRGM | ADOT | 0 | 11440
Angela Ringor | R069229P | MPDR018 | 2017-11-29 | 162 | PAVEMENT MANAGEMENT FORECASTING | ADOT | 697528.04 | 1181031.5
Angela Ringor | R070729P | MPDR018 | 2017-11-29 | 171 | MANAGED LANES/TOLL ROADS | ADOT | 181225 | 407756.25
Angela Ringor | R071829P | MPDR018 | 2017-06-15 | 162 | TRIBES IN TRANSPORTATION DECISION | ADOT | 0 | 9993.88
Angela Ringor | R075430P | MPDR018 | 2017-11-29 | 171 | 17WP MPD RESRCH | ADOT | 0 | 412500
Angela Ringor | R076001P | MPDR018 | 2017-11-29 | 171 | RESEARCH PEER EXCHANGE | ADOT | 0 | 28000
Angela Ringor | R076101P | MPDR018 | 2017-11-29 | 171 | EVAL POLLUTANTS FRM ADOTS STORM SYS DISCHARGE | ADOT | 0 | 325000
Angela Ringor | R076201P | MPDR018 | 2017-11-29 | 171 | EFFECTIVNESS AND COSTS OF RDSD SHLDR BLD UP TREATM | ADOT | 0 | 365000
Angela Ringor | R076301P | MPDR018 | 2017-12-11 | 167 | SPR-763 Eval of Intersection Safety AZ Hwy Sys | ADOT | 0 | 250000
Angela Ringor | R076401P | MPDR018 | 2017-12-13 | 167 | SPR-764 Eco Impact of AZ Hwy Mag | ADOT | 0 | 200000
Angela Ringor | R076501P | MPDR018 | 2017-12-13 | 167 | SPR-765 Informing New ADOT Strat for Meeting FED | ADOT | 0 | 200000
Angela Ringor | R140901P | TPF5348 | 2016-06-21 | 162 | I-10 WESTERN CONNECTED FREIGHT CORRIDOR PROJECT | ADOT | 315855 | 315855
Tricia Brown | SE59001D | LLA0207 | 2016-06-03 | 162 | PLOMOSA ROAD MP 8.5 - 20 | ADOT | 0 | 10813.55
Kirstin Tvedten | SF03401C | PPM0242 | 2016-06-08 | 164 | SUMMIT ST: OLD NOGALES HGWY TO EPPERSON LN, TUCSON | Pima County | 254176.19 | 296488.19
Eric Prosnier | SH53103D | SCT0217 | 2012-06-27 | 162 | HAYDEN RD & THOMAS RD; INT. SAFETY IMPROVEMENTS | Scottsdale | 0 | 35912.66
Suzanne Deitering | SH63503D | GLN0246 | 2014-06-27 | 176 | 59TH AVENUE AND OLIVE AVENUE | ADOT | 20.01 | 10862.69
Tricia Brown | SH64101C | MAR0204 | 2016-09-15 | 163 | MARICOPA - SIGN MGMT. SYSTEM/REG. WARNING UPGRADE | ADOT | 0 | 87080.63
Kirstin Tvedten | SL63801D | TUC0 | 2011-11-01 | 176 | PARK AVENUE FROM SPEEDWAY BLVD. TO FT. LOWELL RAD | Tucson | 0 | 1391.89
Vicki Bever | SR21401X | SLP0201 | 2015-08-31 | 174 | VARIOUS COUNTIES-UP | ADOT | 1481.88 | 22922.85
Kirstin Tvedten | SS62401C | TUC0201 | 2016-06-09 | 161 | HOUGHTON ROAD (I-10 TO GOLF LINKS ROAD) | Tucson | 0 | 7172283.62
Susan Webber | SS99003D | GGH0203 | 2011-08-19 | 162 | REAY LANE/SAFFORD-BRYCE ROAD INTERSECTION REALIGNM | ADOT | 0 | 17347.59
Eric Prosnier | SZ04601R | MMA0239 | 2012-07-06 | 167 | NORTHERN PARKWAY: DYSART ROAD TO 111TH AVENUE | Maricopa County | 0 | 3037847.58
ADOT Resource Admin | SZ06801R | PAY0203 | 2015-08-04 | 161 | E BONITA ST: SR 87 to BENTLEY ST | ADOT | 0 | 0
Eric Prosnier | SZ13101C | TMP0238 | 2015-07-30 | 174 | CONST/INST FIBER OPTIC COMM W/ WIRELESS RADIO/CCTV | Tempe | 0 | 197.58
Adam McGuire | SZ13701C | PHX0293 | 2016-08-31 | 168 | RIO SALADO PATHWAY: 32ND STREET TO 40TH STREET | Phoenix | 3170173.56 | 3361794.99
Thomas O'Reilly | SZ15501D | SRI0 | 2015-02-11 | 154 | SALT RVR PIMA-MARICOPA INDIAN PEDESTRIAN PROJECT | ADOT | 0 | 5.59
Adam McGuire | SZ17501D | PHX0 | 2015-06-24 | 162 | 107TH AVE; CAMELBACK RD - INDIAN SCHOOL RD, PHX | Phoenix | 0 | 471.85
Adam McGuire | T001201D | PHX0 | 2016-02-24 | 176 | PAVE DIRT ALLEYS - PHOENIX | Phoenix | 0 | 5372.54
Kirstin Tvedten | T003401D | AVN0224 | 2016-08-16 | 176 | MCDOWELL RD - DYSART TO AVONDALE BLVD | ADOT | 0 | 2
Eric Prosnier | T010001D | SCT0 | 2016-07-20 | 176 | VAR LOCATIONS - SCOTTSDALE TRAFFIC CABINET UPGRADE | Scottsdale | 0 | 191.26
Eric Prosnier | T015901D | TMP0 | 2017-10-04 | 178 | UPR Tempe South Spur Line University Dr-BaselineRd | Tempe | 0 | 10000
26367072.96