*		USE IN CONJUNCTION WITH BID ITEM:	7010005		*

*** TEMPORARY STRIPING USED AS TRAFFIC CONTROL SHOULD BE PART OF THE COST OF THIS ITEM. 708 PAY ITEMS ARE ONLY FOR INTERIM STRIPING AND NOT TEMPORARY STRIPING. DO NOT INCLUDE THE QUANTITY OF TEMPORARY STRIPING IN 708 ITEMS. ***

(701LUMPSUM, 03/20/25)

SECTION 701 	MAINTENANCE AND PROTECTION OF TRAFFIC:

701-1			Description:  the first paragraph of the Standard Specifications is revised to read:

The work under this section shall consist of providing flagging services and pilot trucks, and furnishing, installing, maintaining, moving and removing barricades, warning signs, lights, signals, cones, temporary pavement markings and other traffic control devices to provide safe and efficient passage through and/or around the work and to protect workers in or adjacent to the work zone.  The work shall be done in accordance with the requirements of Part 6 of the Manual on Uniform Traffic Control Devices (MUTCD) and the associated Arizona Department of Transportation supplement.  When referred to herein, these documents will be referred to as MUTCD and associated ADOT Supplement.

701-1			Description:  the third paragraph of the Standard Specifications is revised to read:

Any traffic control plan included in the project plans shall govern unless an alternate plan, acceptable to the Engineer, is submitted by the contractor.  If no traffic control plan is provided or if the contractor desires to deviate from the provisions for maintaining traffic as described in this section, it shall submit to the Engineer for the approval of a proposed sequence of operations and a compatible method of maintaining traffic.

701-3.01			General: of the Standard Specifications is modified to add:

At the preconstruction conference the contractor shall submit a log of all existing signs within the limits of the construction zone.  The Department will verify the accuracy of the sign log.  Throughout the duration of this project, all existing traffic signs shall be maintained by the contractor in accordance with Subsection 701-3.11 of the specifications.

The contractor shall coordinate all traffic control work on this project with any adjoining or overlapping projects during the construction activities.  This may include barricade placement necessary to provide a uniform traffic progress.

701-4.01		General:  the first paragraph of the Standard Specifications is revised to read:

The Department will reimburse the contractor for the work of maintaining and protecting traffic on a lump sum basis except for the following Elements of Work:

- Changeable Message Boards

- Temporary Impact Attenuation Devices

- Temporary Concrete Barrier

- Specialty Signs

- Local Enforcement Officers

- DPS Officers

- Civilian Flaggers

- Pilot Vehicles

- Truck-Mounted and Trailer-Mounted Attenuators

No additional measurement for payment to the contractor will be made for any Elements of Work other than those listed above.

701-4.01	General:  the first sentence of the third paragraph of the Standard Specifications is revised to read:

Elements of Work except those reimbursed under the lump sum item will be measured for payment as follows:

701-4.03(E)	Limitation of Measurement:  the second paragraph of the Standard Specifications is revised to read:

For all items except those reimbursed under the lump sum item, measurement will be made after the initial installation and once weekly thereafter for items in continuous use and at any other times changes are made in the use of traffic control elements listed under Subsection 701-4.01(B) of the specifications.  The contractor shall notify the Engineer when any changes are made in the use or location of traffic control elements.

701-4.04		Measurement of Work Elements:  Sub-paragraphs (D), (G), (H), (J), (K), (L), and (N) of the Standard Specifications are hereby deleted.

701-5			Basis of Payment for Elements of Work (Complete–in-Place): of the Standard Specifications is modified to add:

All elements of work necessary for the work of maintaining and protecting traffic, excluding Elements of Work listed in Subsection 701-4.01 of the specifications, shall be reimbursed as a single, complete item of work, which price shall be considered full compensation for the work, complete in place, including furnishing, removing, setting up, relocating, taking down, maintaining, and storing the devices.

Lump sum traffic control will be paid according to the schedule shown in Table 701-5 of the specifications.

| Table 701-5 Payment Schedule for Lump Sum Traffic Control |  |
| --- | --- |
| Percent of Total Contract Amount Earned (Excluding Mobilization and Traffic Control) | Allowable Percent of Lump Sum Price for Maintenance and Protection of Traffic |
| 5 | 20 |
| 25 | 40 |
| 50 | 60 |
| 75 | 80 |
| 90* | 100 |
| *Or substantial completion |  |

If the Engineer determines that the final contract amount earned will fall between 75 and 100 percent of the original contract amount, lump sum traffic control will be compensated at 100 percent once final acceptance is achieved.

In the event the Department revises the contract in accordance with Subsection 104.02 of the specifications due to a significant change in the character of work, and the revisions impact the Maintenance and Protection of Traffic, the lump sum price for Maintenance and Protection of Traffic will be adjusted as part of the contract revision under the relevant supplemental agreements.

No adjustments to the lump sum price for Maintenance and Protection of Traffic will be made for suspension of work for seasonal restrictions.

Revisions in the phasing of construction or maintenance of traffic control operations, requested by the contractor, may require traffic control to be installed in accordance with standards and/or designs other than those included in the plans.  Such revisions or modifications to the traffic control plans shown in the contract shall be submitted by the contractor for approval by the Engineer. No additional payment will be made for the revised plans requested by the contractor.

701-5.03 		Temporary Preformed Markings for Pavement:  of the Standard Specifications is hereby deleted.

701-5.05 		Obliterate Pavement Marking:  of the Standard Specifications is hereby deleted.

701-5.06 		Temporary Pavement Markers and Chip Seal Pavement Markers:  of the Standard Specifications is hereby deleted.

701-5.07 		Obliterate Pavement Markers:  of the Standard Specifications is hereby deleted.

701-5.08 		Temporary Delineators:  of the Standard Specifications is hereby deleted.

701-5.10		Temporary Removal or Covering of Signs:  of the Standard Specifications is hereby deleted.

701-6.01		Quantity Variances:  of the Standard Specifications is revised to read:

Payment for variances in quantities of items listed in Subsection 701-4.01 of the specifications shall be in accordance with Subsection 104.02 of the specifications, except that, for decreases in quantities, Temporary Concrete Barrier (In-Use) will be considered as a major item.

701-6.03		Channelization Devices:	of the Standard Specifications is hereby deleted.

701-6.04		Temporary Signs:  of the Standard Specifications is hereby deleted.

701-6.06		Flashing-Arrow Panels, and Changeable Message Boards:  the title and text of the Standard Specifications are revised to read:

701-6.06		Changeable Message Boards:

The accepted quantities of changeable message boards, measured as provided above, will be paid for at the unit bid price per day, which price shall be full compensation for the work, complete, including any grading and furnishing, operating, maintaining, and relocating the boards on the work site.