(109WFADF, 05/15/25)

SECTION 109	MEASUREMENT AND PAYMENT:

109.04(D)(6)	Statements: the title and text of the Standard Specifications is revised to read:

109.04(D)(6)	Forms:

The contractor shall prepare the Weekly Force Account Detail form for each week of force account activity.  The Weekly Force Account Detail form is a standardized, fillable form made available by the Department on the ADOT Construction Group’s website.

The form shall detail the labor, equipment, and material charges utilized to accomplish the force account work along with all supporting documentation.  The contractor shall furnish copies of original receipts (paid invoice cost) for materials, rental equipment cost, including freight and transportation charges, copies of rental rate blue book equipment sheets and certified payrolls.

If materials used on the force account work are not specifically purchased for such work but are taken from the contractor's stock, then instead of invoices, the forms shall contain or be accompanied by an affidavit of the contractor certifying that such materials were taken from stock, that the quantity claimed was actually used, and that the price and transportation claimed represent the actual cost to the contractor.

Force account work shall be tracked daily; however, the contractor shall compile no more than one full week’s worth of daily records into a Weekly Force Account Detail form.  Each reporting period runs from Saturday through Friday. The contractor shall submit the form within 30 calendar days of the respective week’s force account performance. The completed form shall be submitted to the Engineer for review and approval.  The Engineer will review the form and supporting documentation against the ADOT Inspector’s Daily Force Account Reports, and will verify that the form is timely, complete, and accurate.  Payment will not be made until the contractor has furnished applicable forms, detailing the costs of the force account work, including but not limited to the following information:

- Labor: name, classification, date, daily hours, hourly rate and fringe rate, and certified payrolls for each foreman and laborer.

- Equipment: dates, equipment number, description, operator name, hours used, approved stand-by hours, monthly rental rate, hourly operating cost and rental rate blue book sheets for each unit of equipment.

- Rental Equipment (Third Party): invoice, dates used, vendor name, description of equipment, operator name, hours used, invoice rate, hourly operating cost and rental rate blue book sheets for each rental equipment.

- Materials: invoice, date used, supplier name, description, quantity, unit of measure and unit cost.

- Transportation: freight and express charges on materials, FOB jobsite.