*USE IN CONJUNCTION WITH STORED SPECIFICATION 404BITUM*

* USE ON ALL PROJECTS IN WHICH THE FOLLOWING ARE SEPARATE PAY ITEMS: *

**PG GRADE ASPHALT BINDER**

**EMULSIFIED ASPHALT**

**ASPHALT RUBBER MATERIAL**

*ALSO USE ON ALL PROJECTS WITH ASPHALTIC CONCRETE *

(109BITUMADJ, 06/19/25)

SECTION 109	MEASUREMENT AND PAYMENT:  of the Standard Specifications is modified to add:

109.16		Bituminous Price Adjustment:

- General:

The term "bituminous material" as used herein shall include asphalt binder, asphalt rubber and emulsified asphalt.

The Department will adjust monthly progress payments as appropriate for market fluctuations in the price of bituminous material.

A price for bituminous material will be determined monthly by the Department based on the selling prices published by the Asphalt Weekly Monitor, a publication of Poten & Partners, Inc.  The price will be the arithmetic average of the high and low selling prices for bituminous material shown in the previous four reports for the Arizona/Utah and Southern California regions.

This value will be effective as of the last Wednesday of each month, and will be posted on the ADOT Contracts and Specifications Group website, on or shortly after the last Wednesday of each month.

This price will be deemed the “initial cost” (IC) for bituminous material for projects on which bids are opened during the following month.  This price will also be deemed the "current price" (CP) for bituminous material for the following month for projects in construction.

- Measurement:

For each item of bituminous material for which there is a specific pay item, and for the bituminous material used in Asphaltic Concrete mixes, an adjustment will be made for each month that a quantity of bituminous material was used on the project.

The IC for the month in which the project was bid will be compared with the CP for the appropriate current month.  The CP will be as posted on the Department’s website on the last Wednesday of each month, and will be used to adjust costs for bituminous material incorporated into the job during the following month (for example; bituminous material used in May will be adjusted, as specified herein, based on the CP for May as posted on the last Wednesday of April).  Any difference in price between these two values will be applied to the quantity of eligible bituminous material incorporated into the work.

Determination of the eligible quantities of bituminous material for adjustment will be based on contractor-furnished invoices, except as described herein.

The tons of emulsified products to which the adjustment will be applicable will be the tons of the emulsified asphalt prior to dilution.

Adjustments in compensation for emulsified asphalts will be made at 60 percent of either the increase or decrease of IC.  For emulsified asphalts containing polymer, adjustments in compensation will be made at 66 percent of either the increase or decrease.

The tons of Bituminous Material (Asphalt-Rubber) to which the adjustment is applicable will be 80 percent of the total quantity of the item used.  The adjustment is not applicable to the 20 percent of the material which constitutes the crumb-rubber additive.

The tons of Bituminous Material (TR+) to which the adjustment is applicable will be 92 percent of the total quantity of the item used.  The adjustment is not applicable to the 8 percent of the material which constitutes the crumb-rubber additive.

The tons of bituminous material in Asphaltic Concrete mixes, subject to price adjustment shall be calculated as follows, based on the approved mix design target values and the quantity of Asphaltic Concrete placed—regardless of the actual percentage of binder incorporated:

A monthly adjustment, if applicable, will be made on this quantity, as shown below:

PA = (CP – IC) x ACP x F

Where:	PA = Price Adjustment monetary amount (plus or minus in dollars)

CP = Current index price (dollars per ton)

IC = Initial Cost at time of bid (dollars per ton)

ACP = Asphaltic Concrete Placed (tons)

F = Eligible Asphalt Cement %

The value calculated above (plus or minus) will be adjusted to include sales tax and other taxes as applicable.

- For mixes without reclaimed asphalt pavement (RAP):

F = Approved Mix Design Target Asphalt Cement %

(2)	For mixes with RAP:

F = Approved Mix Design Target Asphalt Cement % – Mix Design RAP Asphalt Cement contribution %

(3)	For mixes using PG TR+ Terminal Blend (8 % Crumb Rubber):

F = 0.92 x (Approved Mix Design Target Asphalt Cement %)

(4)	For mixes using Asphalt-Rubber Blend (20 % Crumb Rubber):

F = 0.80 x (Approved Mix Design Target Asphalt Cement %)

(5)	If the quantity of Asphaltic Concrete is measured by volume, the supplemental agreement establishing the method of measurement will specify the manner in which the tons of bituminous material eligible for the adjustment is determined.

(C) 	Payment:

Price adjustments will be shown on the monthly progress estimate, but will not be included in the total cost of work for determination of progress or for extension of contract time.

Price adjustments will be calculated using the measurement methods described above. Only the tons of virgin asphalt binder determined by those methods will be subject to a bituminous material price adjustment.

No price adjustment will be made for the RAP binder in the mix.

No price adjustment will be made for the 8% of binder comprising crumb rubber when (TR+) is used.

No price adjustment will be made for the 20% of binder comprising crumb rubber in the asphalt-rubber material blend.

No compensation will be made for changes that may have occurred since the time of bidding and which may be the result of any increase in the IC of bituminous material.

Adjustment in unit prices of items governed by this provision will be made in the next regular monthly progress payment following actual use or application of the bituminous material.