**          USE THIS SPECIFICATION ON PROJECTS INVOLVING BORROW,         **

**         SUBBASE, BASE, MATERIALS FOR CONCRETE STRUCTURES, AND   **

**            SURFACING MATERIALS.                                                                          **

**         USE IN CONJUNCTION WITH STORED SPECIFICATION 1001MATL.        **

(104ENVIR, 06/17/21)

SECTION 104	SCOPE OF WORK:

104.12		Environmental Analysis:  the fifth and sixth paragraphs of the Standard Specifications are revised to read:

If the contractor elects to do an environmental analysis and use any site, source, or access for the reasons listed above, they choose to do so at their own risk. It is the contractor’s responsibility to exercise due diligence when selecting these sites and areas. The contractor shall bear all costs associated with the use of proposed sites, sources, and accesses.

The contractor shall promptly advise the Engineer that it is preparing the environmental analysis and shall submit to the Engineer for review and consultation.   The Department will review the submittal and send it to the appropriate agencies and/or jurisdictions for consultation or return it to the contractor for revision. The contractor shall allow a minimum of 60 calendar days after submittal, or subsequent resubmittals, to the Department for the Department to review the environmental analysis and to consult with the appropriate jurisdictions and/or agencies.  At the end of the review period, the Engineer will notify the contractor whether or not the environmental analysis is acceptable.

If the approval of the environmental analysis causes a delay to a controlling activity of the project due to the Department’s actions in the aforementioned review process, the contractor may seek, and the Engineer may grant, an extension of time in accordance with the terms of Subsection 108.08 of the specifications.  The time extension shall not exceed 30 working days for a working-day contract, or 45 calendar days for a calendar-day project.  The time extension will not be considered unless the contractor can show evidence of the delay resulting due to the Department’s actions in the review process. A time extension request will not be considered or granted for any other reason. No time extension will be granted for a fixed completion date contract.

104.12		Environmental Analysis:  the items (G) and (O) of the seventh paragraph of the Standard Specifications is revised to read:

(G)	The archaeological survey of the proposed source prepared by a person who meets the Secretary of the Interior's Professional Qualification Standards (48 FR 44716) and possesses a current permit for archaeological survey issued by the Arizona State Museum (ASM).  The survey shall be prepared in a State Historic Preservation Office (SHPO) standardized format.  The survey shall identify all historic properties within the area of potential effect (APE), as defined by the National Historic Preservation Act (36 CFR 800.4).  This includes the materials source, processing area, and the haul road.  Additionally, the survey report shall identify the effects of the proposed source on any historic properties within the APE, and recommend measures to avoid, minimize, or mitigate those effects. The survey report shall be prepared by the contractor in accordance with SHPO and ASM formatting style for the Historic Preservation Specialist’s initial review. After the initial review, the Department will consult with the landowner, SHPO, and Tribes for a minimum of 35 days for the final approval of the survey report.

(O)	A description of the impact on federally or state protected or other agency-specific special status wildlife and plants and their habitat, as defined in ADOT’s consultant biological procedures on the Department’s website.  Compliance with the Arizona Native Plant Law shall be coordinated through the Arizona Commission of Agriculture and Horticulture.

104.12		Environmental Analysis:  the eighth paragraph of the Standard Specifications is revised to read:

Guidance and forms for preparing the environmental analysis are available on the Department’s website through the Environmental Planning Group, or by calling Environmental Planning Group at 602-712-7767.