***USE ON ALL PROJECTS***

(108PRCN, 08/19/21)

SECTION 108	PROSECUTION AND PROGRESS:

*** PROJECTS WITHOUT STORED SPECIFICATIONS 108SCHLVL1, 108SCHLVL2 OR 108SCHLVL3, USE THE FOLLOWING OTHERWISE DELETE ***

108.03	Preconstruction Conference: the second paragraph of the Standard Specifications is revised to read:

At the preconstruction conference the contractor shall submit a progress schedule showing the order in which the contractor proposes to carry out the work, the dates on which the contractor and its subcontractors will start the work, including procurement of materials, equipment, etc.; the ordering of articles of special manufacture; the furnishing of drawings, plans and other data required under Subsection 105.03 of the specifications for the review and approval of the Engineer; the inspection of structural steel fabrication; and the contemplated dates for the completion. The schedule shall be in a critical path method format.  No schedule activity shall be shorter than one day or longer than 20 days. The schedule must show interrelationships among the activities, and the controlling items of work throughout the project shall be identified. If requested by the Engineer, the contractor shall furnish information needed to justify activity time durations.  Such information shall include estimated manpower, equipment, unit quantities, and production rates. The schedule shall illustrate the completion of the work not later than the contract completion date.

*** PROJECTS WITH STORED SPECIFICATIONS 108SCHLVL1, 108SCHLVL2 OR 108SCHLVL3, USE THE FOLLOWING OTHERWISE DELETE ***

108.03	Preconstruction Conference: the second paragraph of the Standard Specifications is revised to read:

At the preconstruction conference the contractor shall submit a progress schedule showing the order in which the contractor proposes to carry out the work, the dates on which the contractor and its subcontractors will start the work, including procurement of materials, equipment, etc.; the ordering of articles of special manufacture; the furnishing of drawings, plans and other data required under Subsection 105.03 of the specifications for the review and approval of the Engineer; the inspection of structural steel fabrication; and the contemplated dates for the completion.

*** USE ON ALL PROJECTS ***

108.04	Prosecution and Progress: the third paragraph of the Standard Specifications is revised to read:

At a mutually convenient location and time, the contractor shall meet weekly with the Engineer to discuss construction activities; however, a meeting may be waived if mutually agreed to, due to weather conditions, work progress, or for other reasons. At the meetings, the contractor shall provide the Engineer with a detailed, written schedule of construction activities and phases of work for the current week, forthcoming three week period as well as the construction activities which were performed during the previous week. This schedule shall detail the anticipated start dates and anticipated completion dates of work activities. The weekly schedule should reflect, at a minimum, all activities from the most recently updated project schedule. For work which was completed during the previous week, this schedule shall detail the actual start and completion dates of work activities as well as indicate the status of major ongoing activities. Upon the second occurrence of the contractor failing to provide an accurate schedule as describe herein and after written notification by the Engineer of the first occurrence, the Department will deduct $500 from the contractor’s progress payment per each occurrence thereafter. Minutes of the weekly meetings will be kept by the Engineer and a copy given to the contractor for review and acceptance.