***	USE ON ALL PROJECTS.	***

***	FOR PROJECTS WITH AN ENGINEER’S ESTIMATE	***

***	GREATER THAN $90,000,000, CONTACT CONSTRUCTION	***

***	GROUP TO DETERMINE WHETHER LIQUIDATED	***

***	DAMAGE VALUES SHOULD BE INCREASED.	***

***	IF REVISED, OBTAIN BACKUP DOCUMENTATION FOR THE	***

***  INCREASED LIQUIDATED DAMAGE VALUES FOR PROJECT FILE. ***

(108RSLD, 08/17/23) SECTION 108	PROSECUTION AND PROGRESS:

108.09	Failure to Complete the Work on Time:	the Schedule of Liquidated Damages table of the Standard Specifications is revised to read:

| SCHEDULE OF LIQUIDATED DAMAGES |  |  |  |
| --- | --- | --- | --- |
| Original Contract Amount |  | Liquidated Damages Per Day |  |
| From More Than: | To and Including: | Calendar Day or Fixed Date: | Working Day: |
| $ 0 | $ 500,000 | $ 450 | $ 750 |
| 500,000 | 1,000,000 | 1,000 | 1,800 |
| 1,000,000 | 2,000,000 | 1,600 | 2,100 |
| 2,000,000 | 5,000,000 | 2,200 | 2,400 |
| 5,000,000 | 10,000,000 | 3,200 | 7,100 |
| 10,000,000 | 30,000,000 | 8,000 | 9,600 |
| 30,000,000 | 60,000,000 | 14,600 | 16,900 |
| 60,000,000 | 90,000,000 | 19,900 | 27,860 |
| 90,000,000 | ------- | 26,800 | 37,520 |